## Project Planner
Erasmus +, KA220-HED - Cooperation partnerships in higher education | Erasmus +, KA220-HED - Cooperation partnerships in higher education
Project Number: 2023-1-IT02-KA220-HED-00015873
DigiFunCollab - Developing Digital-Self-Learning Courses in Social Entrepreneurship for the future of collaboration between Universities and Community
Project Planner - Cultural Intervetion for a Disadvantage Community
| Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1 | Project Planning | 1 | 3 | 1 | 1 | 100%
2 | Community contact - info collection | 1 | 4 | 1 | 4 | 100%
3 | Define the cultural intervention (Scenario) | 3 | 5 | 4 | 5 | 100%
a | Human resources | 2 | 8 | 1 | 10 | 100%
b | Materials Procurement | 2 | 8 | 1 | 10 | 75%
c | External services | 9 | 3 | 9 | 3 | 50%
d | Additional finacial support (donations, crowdfunding) | 1 | 12 | 1 | 12 | 100%
4 | Preparation for the implementation + communication | 10 | 12 | 10 | 13 | 0%
5 | Implementation of first cultural event (1) | 13 | 1 | 13 | 2 | 0%
6 | Implementation of the second cultural event (2) | 15 | 1 | 15 | 2 | 0%
7 | Implementation of the third cultural event (3) | 17 | 1 | 17 | 2 | 60%
| Activity 12 | 9 | 3 | 9 | 3 | 0%
| Activity 13 | 9 | 6 | 9 | 7 | 50%
| Activity 14 | 9 | 3 | 9 | 1 | 0%
| Activity 15 | 9 | 4 | 8 | 5 | 1%
| Activity 16 | 10 | 5 | 10 | 3 | 80%
| Activity 17 | 11 | 2 | 11 | 5 | 0%
| Activity 18 | 12 | 6 | 12 | 7 | 0%
| Activity 19 | 12 | 1 | 12 | 5 | 0%
| Activity 20 | 14 | 5 | 14 | 6 | 0%
| Activity 21 | 14 | 8 | 14 | 2 | 44%
| Activity 22 | 14 | 7 | 14 | 3 | 0%
| Activity 23 | 15 | 4 | 15 | 8 | 12%
| Activity 24 | 15 | 5 | 15 | 3 | 5%
| Activity 25 | 15 | 8 | 15 | 5 | 0%
| Activity 26 | 16 | 28 | 16 | 30 | 50%